# 3  Activities and Progress

## 3.1  Completed Activities

The following activities have been completed since the start of the semester:

- The project group was formed, the project was selected, and the initial project-team meeting with DEWA was attended (Weeks 1–2).

- A shared OneDrive folder, a project logbook, the Gantt chart and a shared progress-report document were set up, and the four literature-review areas and report sections were divided among the team members (Section 9).

- The first meeting with the supervisors was held on 30 September 2026 to agree the direction of SDP I and the action plan for the next stage (Section 3.3).

- Literature was searched, screened and reviewed in four areas: XLPE cable insulation and defects, PD fundamentals and measurement, PD signal processing and data representation, and machine-learning and deep-learning classification (Section 2).

- A literature matrix of the main classification studies (Table 1) and a comparison of the three candidate approach families (Table 2) were prepared, giving a provisional shortlist of methods (Section 2.5.4.1).

- Three public PD datasets were identified as possible sources of data for early software work (Section 2.4.4).

## 3.2  Work in Progress

The team is completing this combined literature review and progress report. In parallel, the following work is under way:

- Confirming with the laboratory which defect types can be prepared safely and measured reliably, so that the provisional classes (Section 2.5.1.1) can be fixed.

- Reviewing the public datasets for relevance, format and labelling, and recording the source of each one, as requested by the supervisors.

- Deepening the review of the shortlisted methods, so that the input representation and model can be selected at the end of SDP I.

- Preparing the material for the second supervisor meeting.

A simple baseline in Jupyter using suitable public data remains planned for this semester, depending on the availability and relevance of the data.

## 3.3  Progress Against the Project Plan

The project is on schedule against the SDP I Gantt chart (Figure 8). All tasks planned for Weeks 1–5 were completed on time (tasks 1.1–1.17). These ran from forming the group and selecting the project to searching, screening and organising the literature. The only change was the first supervisor meeting (task 1.18). It was planned for Week 5 but was postponed and held on 30 September (Week 6). This did not delay the rest of the work, because the literature review continued in the meantime.

Since that meeting, the team has completed the main items the supervisors asked for: the problem statement (Section 2.1), the literature matrix (Table 1) and the comparison of the three approach families (Table 2). The remaining items are planned for the rest of the semester: the dataset inventory, the final choice of method and a first baseline in Jupyter. The dataset inventory depends on which defects the laboratory can prepare, so it is the item most likely to be delayed.

# 4  Institutional & Project Partner Issues

No issues to report.

# 7  Dissemination

No external dissemination has taken place yet, because the project is still in the literature-review stage and has not produced results. Within the project, findings are shared through the team’s shared OneDrive folder and weekly meetings, with the supervisors at progress meetings (the first on 30 September 2026), and through this progress report.

Planned dissemination:

- Regular progress updates to the university supervisors and the DEWA R&D Centre supervisors.

- The SDP I final report and presentation at the end of this semester.

- The SDP II final report, presentation and poster at the end of the project.

- Documented Jupyter notebooks and a description of every dataset used, including its source, shared with the supervisors and DEWA. Any wider release will depend on their approval.

- If the results allow, a conference or journal paper, prepared with the supervisors.

# 12  Conclusion

This progress report has presented the work completed in the first half of SDP I on the pattern recognition of insulation defects in XLPE cables using PD measurements and deep learning. PD is a reliable indicator of insulation defects, and identifying the type of PD gives more information about the defect than detecting its presence alone.

The literature review covered PD fundamentals and measurement, XLPE cable insulation and defects, PD signal processing and data representation, and machine-learning and deep-learning classification. It showed that both traditional and deep-learning classifiers can exceed 95% accuracy on clean laboratory data. However, accuracy can drop sharply when noise is present or when the model is tested on new specimens, and a high overall accuracy can hide weak classes. These findings will shape how the project evaluates its models. A provisional shortlist of methods has been drawn up: an SVM and a random forest as baselines, a 1D CNN on raw HFCT pulses, an LSTM on sequences of PD cycles, and a 2D CNN on PRPD patterns if a phase reference is available.

The project is on schedule. For the rest of the semester, the team will:

- study the shortlisted methods in more depth;

- confirm with the laboratory which defects can be prepared;

- review the public datasets;

- build a first baseline in Jupyter.

The final choice of method will be made at the end of SDP I, and the experimental work will follow in SDP II. In the longer term, the classifier is intended to support continuous condition monitoring and early warning of insulation failure.

## Suggested addition to Section 9 – Collaboration and Support

(For Section 9: paste after the existing paragraph.)

The contribution of each member to this report is summarised in Table 3.

Table 3. Contribution of each team member to this report.

| Member | Literature review | Other sections of this report |
| --- | --- | --- |
| Mariam Alhosani | 2.4 PD diagnosis, data and signal representation | 1 Summary; 10 Financial statement |
| Zainab Alkhalsan | 2.5 Machine learning and deep learning for PD classification | 3 Activities and progress; 4 Institutional and project partner issues; 7 Dissemination |
| Ayesha Alameri | 2.2 Partial discharge fundamentals and measurement | 5 Outcomes and lessons learned; 6 Evaluation; 9 Collaboration and support |
| Bashayer Alyammahi | 2.3 Power cable insulation and defects | 8 Risks, issues and challenges; 11 Next steps (against Gantt chart) |