## 3.3  Progress Against the Project Plan

Progress is measured against the SDP I Gantt chart (Figure 8) and the action plan agreed at the first supervisor meeting on 30 September 2026.

Gantt chart. All set-up and literature-search tasks planned for Weeks 1–5 (tasks 1.1–1.17) were completed on time. The first supervisor meeting, planned for Week 5 (task 1.18), was postponed and held on 30 September (Week 6). This one-week delay did not hold up other work, because the literature review continued in parallel.

Supervisor action plan. Table 3 shows the status of each item requested at the first meeting.

Table 3. Status of the action plan agreed at the first supervisor meeting.

| # | Action | Deliverable | Status |
| --- | --- | --- | --- |
| 1 | Finalise the problem statement and its importance | Literature-backed problem statement | Completed (Section 2.1) |
| 2 | Build the literature comparison matrix | Comparison table | Completed (Table 1, Section 2.5.4) |
| 3 | Audit the current data | Dataset inventory | In progress. No laboratory measurements are available yet; the inventory will be completed once the defect samples are prepared |
| 4 | Search for additional real PD data | Candidate datasets with source records | In progress. Three public datasets identified (Section 2.4.4) |
| 5 | Compare the three recognition approaches | Method-selection matrix | Completed (Table 2, Section 2.5.4) |
| 6 | Select and justify the approach | Documented methodology decision | Provisional shortlist (Section 2.5.4.1); final selection planned for the end of SDP I |
| 7 | Set up the experimentation environment | Jupyter baseline workflow | Not started. Planned for the rest of the semester using public data |
| 8 | Prepare for the next supervisor meeting | Evidence-based update | In progress |

Overall, the literature-review and method-comparison work is on schedule. The items still open depend mainly on information from the laboratory: the defect types that can be prepared, and the list of items and costs from the laboratory supervisor (Section 10.2).

## 7  Dissemination

No external dissemination has taken place yet, because the project is still in the literature-review stage and has not produced results. Within the project, findings are shared through the team’s shared OneDrive folder and weekly meetings, with the supervisors at progress meetings (the first on 30 September 2026), and through this progress report.

Planned dissemination:

- Regular progress updates to the university supervisors and the DEWA R&D Centre supervisors.

- The SDP I final report and presentation at the end of this semester.

- The SDP II final report, presentation and poster at the end of the project.

- Documented Jupyter notebooks and a description of every dataset used, including its source, shared with the supervisors and DEWA. Any wider release will depend on their approval.

- If the results allow, a conference or journal paper, prepared with the supervisors.

## Suggested addition to Section 9 – Collaboration and Support

(Paste after the existing paragraph. Fill in the sections for the other members.)

The contribution of each member to this report is summarised in Table 4.

Table 4. Contribution of each team member to this report.

| Member | Literature review | Other sections of this report |
| --- | --- | --- |
| Zainab Alkhalsan | 2.5 Machine learning and deep learning for PD classification | 3.3 Progress against the project plan; 7 Dissemination |
| Mariam Alhosani | [section] | [sections] |
| Ayesha Alameri | [section] | [sections] |
| Bashayer Alyammahi | [section] | [sections] |